Annex no. 1

To the National Waste Management

Strategy in the Republic of Moldova (2013-2027)

Action Plan on National Waste Management Strategy implementation in the Republic of Moldova

| General actions on waste management |
| --- |
| Action | Dead-line | Responsible persons | Total estimated costs (lei/euro) | Source of funding (lei) | Monitoring indicators |
| 1 | 2 | 3 | 4 | 5 | 6 |
| General objective 1: To develop integrated municipality waste management systems by harmonizing the legal, institutional and regulatory framework with the EU standards, based on regional approach (geographic location, economical development, existence of access roads, pedological and hydrologic conditions, number of inhabitants, etc.) and territorial division of the country into 8 waste management regions |
| Specific objective 1: To harmonize national law and policy in waste management with the European policies and legislative provisions |
| 1. To asses the costs of implementing the EU Directives on waste management indicated in the national plan for approximation of legislation in the field of environmental protection. | 2013-2014 | Ministry of Environment | 1 550 790/ 100 000 | 1 550 790 (external aid) | Estimated and developed costs of implementing EU Directives on waste management. |
| 2. To develop the Law on Waste | 2013 | Ministry of Environment |  |  | Developed Law on Waste |
| 3. To develop the integrated solid waste management strategy in the Northern Development Region and Central Development Region | 2013-2014 | Ministry of Environment ; Local public authorities | 3 721 896/ 240 000 | 620.316 (FEN) 3.101.500 ( external aid ) | Approved solid waste management strategy in the Northern Development Region and Central Development Region |
| Specific objective 2: To establish the national legal framework in the field of waste management |
| 1. To develop the Government Decision on approving the List of waste, including dangerous waste. | 2013-2014 | Ministry of Environment |  | Twining | Developed Government Decision on approving the List of waste. |
| 2. To develop the authorisation procedure for waste management activities, including dangerous waste. | 2013-2014 | Ministry of Environment |  |  | Developed regulation on authorizing waste management activities, including dangerous waste. |
| 3. To develop the waste management record keeping modality, including dangerous waste. | 2013-2014 | Ministry of Environment; National Bureau of Statistics | 6 823 476/ 440 000 | 620.316 (FEN) 6.203.160 ( external aid ) | Developed act and deed (instruction, regulation). |
| 4. To develop a regulation on waste storage. | 2013-2014 | Ministry of Environment | 155 079/ 10 000 | 155.079 (FEN) | Worked out regulation on waste storage. |
| To develop construction standards for designing, building and commissioning landfills. | 2013-2014 | Ministry of Regional Development and Constructions; Ministry of Environment | 155 079/ 10 000 | 155.079 (FEN) | Developed legislative act. |
| 6. To develop the procedure of creating intercommunity waste management associations. . | 2013 | Ministry of Environment ; Local public authorities | 77 540/ 5 000 | 77.540 (FEN) | Worked out order of the Minister of Environment on approving the procedure creating waste management associations. |
| 7. To develop norms on establishing waste collection and disposal taxes. | 2014-2015 | Ministry of Environment ; Ministry of Economy; Local public authorities |  |  | Developed legislative act. |
| 8. To develop and implement economic and financial mechanisms according to producer responsibility principle for all the waste flows, including the special ones: accumulators and batteries, used oils, used tires, packages, electric and electronic equipments, disused vehicles, etc. | 2014-2016 | Ministry of Environment; Ministry of Finance | 1 705 869/ 110 000 | 155.079 (FEN) 1.550.790 ( external aid ) | Developed and implemented economic and financial mechanisms. |
| 9. To improve the current system of collecting, processing and analysing data and information on waste management based on the List of waste, including dangerous waste. | 2014-2015 | Ministry of Environment ; National Bureau of Statistics; Local public authorities | 4 807 449/ 310 000 | 155.079 (FEN) 4.652.370 ( external aid ) | Developed information system (number of worked out programs). |
| Specific objective 3: To enforce institutional capacities at national and regional level on waste management for attracting investments in implementing the National Strategy of Waste Management |
| 1. To delegate the Environmental Pollution Prevention Division and functions of development and implementation of investments projects for the waste sector. | 2013-2014 | Ministry of Environment Pollution Prevention Division; Local public authorities |  |  | Developed Order of the Ministry of Environment on Delegating functions of development and implementation of investments projects. |
| 2. To create intercommunity (inter-district) associations for implementing an integrated waste management at an intercommunity/ inter-district level in the regions. | 2013-2015 | Ministry of Environment; Local public authorities |  |  | Number of created associations |
| 3. To develop professional trainings on waste management, including dangerous waste, at all the levels both in the private and in the public sector | 2014-2017 | Ministry of Environment; Local public authorities | 775 395/ 50 000 | 775.395 (FEN) | The number of developed professional trainings. |
| 4. To organise trainings on the implementation of the new data reporting system on waste management, including dangerous waste. | 2014-2015 | Ministry of Environment ; National Bureau of Statistics; Local public authorities | 1 783 409/ 115 000 | 232.618 (FEN) 1.550.790 ( external aid ) | The number of organised seminars. |
| Specific objective 4: To promote a system of information, raising awareness and motivation for all the parties, including enterprises involved in waste management and their impact, including waste that is dangerous for the population and the environment. |
| 1. To develop a communication strategy between parties involved in the management of all kind of waste. | 2014-2015 | Ministry of Environment | 77 540/ 5 000 | 77.540 (FEN) | Community strategy between all the parties involved in management of all kind of waste developed by Order of the Ministry of Environment. |
| 2. To organise and hold education and raising awareness programs on “producer responsibility obligation” and polluter pays principle. | Permanently | Ministry of Environment | 1 705 869/ 110.000 | 155.079 (FEN) 1.550.790 ( external aid ) | Number of organised and worked out programs of education and raising awareness. |
| 3. To organize awareness raising campaigns on the impact of poor waste management, including waste that is dangerous from the environmental point of view. | Permanently | Ministry of Environment ; Ministry of Healthcare | 12.561.399/ 810.000 | 155.079 (FEN) 12.406.320 ( external aid ) | Number of raising awareness campaigns. |
| General objective 2: To develop a regional infrastructure of storing solid household waste |
| Specific objective 1: To ensure the servicing of as many as possible generators of waste collection and transportation systems |
| 1. To extend the waste collection and disposal enterprises from urban areas into rural areas. | 2013-2015 | Ministry of Environment; Local public authorities |  |  | Number of waste collection and disposal services at district level. |
| 2. To create waste collecting systems in the urban/rural area by purchasing containers and installing transfer stations, and introducing and extending selective collecting to the source. | 2013-2016 | Ministry of Environment, Local public authorities | 139.571.100/ 9.000.000 | 46.523.700 (FEN) 93.047.400 ( external aid ) | Number of purchased containers and installed transfer stations. |
| 3. To create optimal schemes by providing every region with specialised means of transport. | 2013-2016 | Ministry of Environment ; Local public authorities; Ministry of Transport and Road Infrastructure | 651 331 800/ 42 000 000 | 186.094.800 (FEN) 465.237.000 (external aid ) | Number of purchased roll-off trucks. |
| 4. To create a system for dangerous waste collection and transportation. | 2015-2017 | Ministry of Environment; Ministry of Transport and Road Infrastructure; Local public authorities | 38.769.750/ 2.500.000 | 7.753.950 (FEN) 31.015.800 ( external aid ) | Number of installed dangerous waste landfills |
| 5. To reduce the number of existing landfills by installing 4-6 intercommunity solid household waste stores at regional level. | 2014-2016 | Ministry of Environment; Local public authorities. | 728.871.300/ 47.000.000 | 682.347.600 (FEN) 46.523.700 ( external aid ) | Number of installed intercommunity solid household waste stores at a regional level. |
| 6. To develop the plan on closing landfills non-conforming with the EU requirements. | 2014-2016 | Ministry of Environment; Local public authorities. | 372.190/ 24 000 | 372.190 (FEN) | The plan on closing landfills non-conforming with the EU requirements. |
| 7. To develop feasibility studies for building 2-3 solid household waste stores in the Southern Development Region. | 2013-2014 | Ministry of Environment; Regional development agencies. | 3.101.580/1 200 000/1 | 3.101.580/1 (external aid ) | Developed feasibility studies. |
| 8. To initiate the construction of solid household waste stores and of build transfer stations. | 2014-2017 | Ministry of Environment; Ministry of Regional Development and Constructions. | 134.686.111/ 8 685 000 | 134.686.111* (external aid ) | Number of solid household waste stores and of build transfer stations. |
| 9. To decontaminate lands historically contaminated with pesticides. | 2013-2017 | Ministry of Environment; Ministry of Agriculture and Food Industry; Local public authorities | 31.015.800/ 2 000.000 | 7.753.950 (FEN) 23.261.850 ( external aid ) | Number of lands historically contaminated with pesticides. |
| 10. To decontaminate lands historically contaminated and currently abandoned. | 2014-2017 | Ministry of Environment ; Local public authorities | 15.507.900/ 1.000.000 | 7.753.950 (FEN) 7.753.950 (external aid ) | Number of decontaminated lands historically contaminated |

Specific actions for specific waste streams

| Action | Dead-line | Responsible persons | Estimated costs (lei/euro) | Sources of funding (lei) | Monitoring indicators |
| --- | --- | --- | --- | --- | --- |
| 2 | 3 | 4 | 7 | 6 | 8 |
| General objective 3: To develop system for collection and treatment of specific waste streams s (packages, WEEE, tires, batteries, etc.) by promoting and implementing the Producer Responsibility Principle, including dangerous waste (medical waste, used oils, etc.), (one landfill per region) |
| Specific objective 1: To create a managing infrastructure for the following waste flows: green waste, alluvial waste, wood waste, packages and uncontaminated waste from constructions and pulling down. |
| 1. To create networks for separate collecting of green waste, animal dejection, wood waste. | 2014-2017 | Ministry of Economy; Ministry of Environment; Local public authorities; NGOs. | 77.539.500/ 5.000.000 | 77.539.500 (FEN) | Number of built waste composting and fermentation facilities. |
| 2. To promote projects on recovery of energy from vegetable waste, where material recovery is not feasible. | 2014-2015 | Ministry of Economy ; Ministry of Environment; Local public authorities. |  |  | Number of promoted projects. |
| 3. To create packaging waste collecting facilities. | 2014-2017 | Ministry of Environment ; Local public authorities. |  | Polluter Pays Principle (PPP)** | The quantity of reused and recovered packages. |
| Specific objective 2: To create a managing infrastructure for the following waste flows: waste resulted from medical activity and research establishments, used oils, used tires, batteries and accumulators, electrical and electronic waste and waste contaminated with dangerous substances from constructions and pulling downs. |
| 1. To create a network for separate infectious waste collection and their pre-treatment prior to disposal. | 2013-2017 | Ministry of Healthcare; Local public authorities. |  |  | Number of medical facilities provided with networks of separate infectious waste collection and their pre-treatment prior to disposal. |
| 2. To create infectious waste disposal facilities. | 2014-2016 | Ministry of Healthcare; Local public authorities | 7.753.950/ 500.000 | 1.550.790 (FEN) 6.203.160 ( external aid ) | Number of infectious waste disposal facilities. |
| 3. To create collecting and storing facilities for dangerous waste. | 2014-2016 | Ministry of Healthcare; Local public authorities | 62.031.600/ 4.000.000 | 62.031.600 (FEN) | Collecting and storing facilities at a regional level. |
| 4. To create a network of used oils collection from users/inhabitants by cooperating with automobile repair shops. | 2014-2016 | Ministry of Environment; Local public authorities. | 6.885.508/ 444.000 | 62.031.60 (FEN) 6.823.476 ( external aid ) | Number of created depots collecting used oils from users/inhabitants. |
| 5. To dispose stocks of used oils through incineration. | 2016 | Ministry of Environment; Local public authorities. |  | PPP | Number of facilities used for disposing stocks of used oils. |
| 6. To create networks for used tires collection by cooperating with automobile repair shops and parkings by 2015. | 2013-2015 | Ministry of Environment; Local public authorities. | 3.101.580/ 200.000 | 3.101.580 (FEN) | Number of created used tires collection depots. |
| 7. To create networks for separate collection of batteries and accumulators form users/inhabitants by cooperating with automobile repair shops by 2015. | 2013-2015 | Ministry of Environment; Local public authorities. | 55.828.440/ 3.600.000 | 55.828.440 ( external aid ) | The collected amount of waste batteries and accumulators. |
| 8. To create separate collection and recovery depots for electrical and electronic waste. | 2014-2017 | Ministry of Environment; Local public authorities. | 201.602.700/ 13.000.000 | 201.602.700 ( external aid ) | Collected amount of electrical and electronic waste. |
| 9. To create facilities for waste contaminated with dangerous substances from constructions and pulling downs with the aim of recovery or disposal. | 2015-2017 | Ministry of Environment; Local public authorities. | 54.277.650/ 3.500.000 | 38.769.750 (FEN) 15.507.900 ( external aid ) | The amount of recovered or disposed waste contaminated with dangerous substances from constructions and pulling downs. |

Total:  2.251.250.827 (MDL)

145.168.000 (Euro)

Costs in euro were calculated according to the National Bank of Moldova official exchange rate of April 17, 2012.

*         According to the integrated strategy of waste management in the Southern Development Region there has been planed to build 3 solid household waste stores, the total cost being 21.237.625 Euro. For the fist stage (2013 - 2017) there has been planned the amount of 8.685.000 Euro.

**      There were no cost estimations for the activities mentioned at pt. 2.1.1. and 4.1.2.as it is the responsibility of economic agents, according to the Polluter Pays Principle.

- No financial sources are needed. The activities will be worked out by employees of the involved establishments.